## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-01 | As a user, I want to register and log in securely so that I can access the procurement system based on my role. | Must Have | User, Authentication | indu | Completed
Sprint 1 | Sprint 1 | US-02 | As an admin, I want to manage users and departments so that users can be assigned appropriate roles and departments. | Must Have | US-01 | gunanithi | Completed
Sprint 1 | Sprint 1 | US-03 | As an employee, I want to create a purchase requisition so that I can request required products or services. | Must Have | US-01, US-02 | chaitanya | Completed
Sprint 1 | Sprint 1 | US-04 | As an employee, I want to select a department and product category while creating a requisition. | Must Have | Department, Product Category | Tarunika | Completed
Sprint 2 | Sprint 2 | US-05 | As a manager, I want to view and approve/reject employee requisitions so that requests can be reviewed before further processing. | Must Have | US-03 | indu | Completed
Sprint 2 | Sprint 2 | US-06 | As a finance user, I want to review approved requisitions so that financial validation can be performed. | Must Have | US-05 | gunanithi | Completed
Sprint 2 | Sprint 2 | US-07 | As a procurement officer, I want to view approved requisitions and generate purchase orders. | Must Have | US-06 | gunanithi | Completed
Sprint 2 | Sprint 2 | US-08 | As an admin, I want to manage suppliers and supplier verification so that only valid suppliers can participate in procurement. | Must Have | US-01 | chaitanya | Completed
Sprint 3 | Sprint 3 | US-09 | As a procurement officer, I want AI-based supplier recommendations so that I can select the most suitable vendor efficiently. | Should Have | Supplier Data, Performance Data | chaitanya | Completed
Sprint 3 | Sprint 3 | US-10 | As a manager, I want to receive alerts for high-priority requisitions so that urgent requests can be handled immediately. | Should Have | US-03, Priority | indu | Completed
Sprint 3 | Sprint 3 | US-11 | As a finance user, I want high-priority request alerts so that urgent financial approvals are not missed. | Should Have | US-10 | Tarunika | Completed
Sprint 3 | Sprint 3 | US-12 | As a procurement officer, I want high-priority request alerts so that urgent procurement requests can be processed quickly. | Should Have | US-10 | Tarunika | Completed
Sprint 3 | Sprint 3 | US-13 | As a procurement officer, I want to compare the top three AI-recommended suppliers before generating a PO. | Should Have | US-09 | Tarunika | Completed
Sprint 3 | Sprint 3 | US-14 | As a procurement officer, I want to use the AI-recommended supplier directly while generating a PO. | Should Have | US-13 | indu | Completed
Sprint 3 | Sprint 3 | US-15 | As a user, I want a consistent dashboard with KPIs, charts, priority information, and theme support so that the system is easy to understand and use. | Could Have | Role Dashboards | chaitanya | Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 168 | 229 | 69 | 37 | 33 | 27 | 21 | 21 | 20 | 0 | 0 | 0 | 0 | 0 | 1
SPRINT 1 BACKLOG
US-01 | T-01 | Implement user registration | TBD | TBD | Indu | Development | Completed | 6 | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | T-02 | Implement login and authentication | TBD | TBD | Gunanithi | Development | Completed | 6 | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | T-03 | Implement role-based access | TBD | TBD | Chaitanya | Development | Completed | 5 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T-04 | Implement department management | TBD | TBD | Indu | Development | Completed | 5 | 6 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T-05 | Implement user management for admin | TBD | TBD | Gunanithi | Development | Completed | 6 | 12 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T-06 | Create employee requisition form | TBD | TBD | Indu | Frontend Development | Completed | 8 | 7 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T-07 | Implement requisition backend APIs | TBD | TBD | Chaitanya | Backend Development | Completed | 8 | 10 | 3 | 0 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US-04 | T-08 | Populate department dropdown | TBD | TBD | Tarunika | Integration | Completed | 3 | 12 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US-04 | T-09 | Populate product category dropdown | TBD | TBD | Tarunika | Integration | Completed | 3 | 12 | 4 | 3 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US-05 | T-10 | Implement manager pending requisition view | TBD | TBD | Indu | Frontend Development | Completed | 6 | 8 | 3 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
US-05 | T-11 | Implement approve/reject functionality | TBD | TBD | Gunanithi | Backend Development | Completed | 6 | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-06 | T-12 | Implement finance requisition view | TBD | TBD | Indu | Frontend Development | Completed | 6 | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-06 | T-13 | Implement finance approval workflow | TBD | TBD | Chaitanya | Backend Development | Completed | 6 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-07 | T-14 | Implement PO generation workflow | TBD | TBD | Chaitanya | Backend Development | Completed | 8 | 6 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-07 | T-15 | Implement Generate PO interface | TBD | TBD | Indu | Frontend Development | Completed | 6 | 12 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
US-08 | T-16 | Implement supplier registration | TBD | TBD | Gunanithi | Backend Development | Completed | 5 | 7 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US-08 | T-17 | Implement supplier verification | TBD | TBD | Gunanithi | Backend Development | Completed | 5 | 10 | 3 | 0 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US-09 | T-18 | Implement supplier recommendation API | TBD | TBD | Tarunika | AI Development | Completed | 8 | 12 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US-09 | T-19 | Implement supplier recommendation scoring | TBD | TBD | Tarunika | AI/Backend Development | Completed | 6 | 12 | 4 | 3 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US-09 | T-20 | Display recommended suppliers in PO modal | TBD | TBD | Indu | Frontend Development | Completed | 6 | 8 | 3 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US-13 | T-21 | Display top three recommended vendors | TBD | TBD | Gunanithi | UI Development | Completed | 5 | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-14 | T-22 | Implement Use AI Recommended Supplier action | TBD | TBD | Tarunika | Frontend Integration | Completed | 4 | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-10 | T-23 | Add high-priority requisition support | TBD | TBD | Tarunika | Backend Development | Completed | 5 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-10 | T-24 | Implement manager high-priority alert | TBD | TBD | Tarunika | Frontend Development | Completed | 5 | 6 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-11 | T-25 | Implement finance high-priority alert | TBD | TBD | Tarunika | Frontend Development | Completed | 4 | 12 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
US-12 | T-26 | Implement procurement high-priority alert | TBD | TBD | Indu | Frontend Development | Completed | 4 | 7 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US-15 | T-27 | Improve dashboard KPI cards | TBD | TBD | Gunanithi | UI Development | Completed | 5 | 10 | 3 | 0 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US-15 | T-28 | Add priority column to requisition tables | TBD | TBD | Chaitanya | UI Development | Completed | 4 | 12 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US-15 | T-29 | Add dashboard charts | TBD | TBD | Tarunika | UI Development | Completed | 6 | 12 | 4 | 3 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US-15 | T-30 | Implement dark/light theme consistency | TBD | TBD | Tarunika | UI Development | Completed | 5 | 8 | 3 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US-15 | T-32 | Make Generate PO recommendation modal scrollable | TBD | TBD | Tarunika | UI Enhancement | Completed | 3 | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | Difficulty understanding the existing project structure | Reviewed frontend, backend and database architecture
Sprint 1 | Day 2 | Department data was not appearing in dropdown | Checked database, API and department configuration
Sprint 1 | Day 3 | Product categories were not populated | Added/verified category data and API integration
Sprint 2 | Day 4 | Supplier data was not appearing in PO workflow | Verified supplier status, category mapping and API response
Sprint 2 | Day 5 | Requisition approval flow required integration across roles | Tested employee → manager → finance → procurement flow
Sprint 2 | Day 6 | PO generation UI required better usability | Improved Generate PO modal
Sprint 3 | Day 7 | Vendor recommendation required meaningful supplier ranking | Implemented weighted recommendation based on supplier factors
Sprint 3 | Day 8 | High-priority requests needed role-specific visibility | Implemented alerts for manager, finance and procurement
Sprint 3 | Day 9 | Dashboard looked inconsistent across roles | Unified KPI cards, charts, priority indicators and themes
Sprint 3 | Day 10 | AI recommendation modal became larger than viewport | Added responsive scrolling
Sprint 3 | Day 11 | Dashboard charts initially lacked meaningful data | Connected charts to actual requisition data
Sprint 3 | Day 12 | Edit requisition functionality required API integration | Fixed update flow and validation
Sprint 3 | Day 13 | Git integration and branch synchronization | Merged feature branch changes into development
Sprint 3 | Day 14 | Final integration verification | Tested application workflows and fixed UI/integration issues

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | TBD | TBD | Indu | Start documenting requirements before development | Stop making assumptions about existing APIs | Continue collaborative development and testing | Maintain requirement tracking and regular team discussions
2 | Sprint 2 | TBD | TBD | Chaitanya | Start testing each role independently | Stop testing only from one user perspective | Continue integration testing | Test employee, manager, finance and procurement workflows
3 | Sprint 3 | TBD | TBD | Tarunika | Start validating UI against real data | Stop using placeholder data for final features | Continue code review and Git collaboration | Perform final integration testing before merging changes
4 | Sprint 1 | TBD | TBD | Gunanithi | Start breaking large requirements into smaller tasks | Stop postponing integration testing until the end | Continue communicating blockers with the team | Tasks were divided into smaller modules and tracked regularly
5 | Sprint 2 | TBD | TBD | Tarunika | Start testing APIs along with frontend development | Stop making UI changes without checking backend dependencies | Continue validating features with real database data | Frontend and backend integration was tested together
6 | Sprint 3 | TBD | TBD | Gunanithi | Start performing final regression testing after every major change | Stop introducing unnecessary changes to working features | Continue maintaining consistent UI and role-based workflows | Final features were tested across Employee, Manager, Finance and Procurement roles